## Projects
Project ID | Project Name | Domain | Status | Priority | Start Date | End Date | Budget (₹) | Spent (₹) | Project Manager | Health Status | % Complete | Budget Utilization % | Days Remaining
PRJ-001 | Customer Portal Redesign | Healthcare | In Progress | High | 2025-01-10 | 2025-06-30 | 850000 | 720000 | Sarah Khan | RAG_Green | 84.7 | 84.7 | 11
PRJ-002 | Payment Gateway Integration | Fintech | In Progress | Critical | 2025-02-01 | 2025-07-15 | 1200000 | 980000 | Raj Mehta | RAG_Amber | 81.7 | 81.7 | 26
PRJ-003 | Mobile App v2.0 | Consumer Internet | Completed | High | 2024-10-01 | 2025-03-31 | 650000 | 648000 | Priya Singh | RAG_Green | 100 | 99.7 | 0
PRJ-004 | Data Warehouse Migration | Healthcare | In Progress | Medium | 2025-03-01 | 2025-09-30 | 950000 | 310000 | Amit Verma | RAG_Red | 32.6 | 32.6 | 103
PRJ-005 | CRM Automation Suite | Fintech | Planning | High | 2025-05-01 | 2025-12-31 | 780000 | 95000 | Neha Sharma | RAG_Green | 7.4 | 12.2 | 195
PRJ-006 | AI Chatbot Integration | Consumer Internet | In Progress | Critical | 2025-01-15 | 2025-08-31 | 1100000 | 870000 | Vikram Nair | RAG_Amber | 79.1 | 79.1 | 73
PRJ-007 | Legacy System Decommission | Healthcare | On Hold | Low | 2025-04-01 | 2025-11-30 | 420000 | 55000 | Deepa Pillai | RAG_Red | 13.1 | 13.1 | 164
PRJ-008 | API Marketplace Launch | Consumer Internet | In Progress | High | 2025-02-15 | 2025-07-31 | 560000 | 390000 | Arjun Das | RAG_Green | 69.6 | 69.6 | 42

## Sprints
Project ID | Sprint Name | Start Date | End Date | Status | Planned Story Points | Completed Story Points | Accepted Story Points | Carried Over Points | Bugs Found | Sprint Predictability %
PRJ-001 | Sprint 1 | 2025-01-13 | 2025-01-24 | Completed | 42 | 42 | 40 | 0 | 2 | 98
PRJ-001 | Sprint 2 | 2025-01-27 | 2025-02-07 | Completed | 45 | 44 | 43 | 1 | 1 | 96
PRJ-001 | Sprint 3 | 2025-02-10 | 2025-02-21 | Completed | 50 | 48 | 46 | 2 | 2 | 92
PRJ-001 | Sprint 4 | 2025-02-24 | 2025-03-07 | Completed | 48 | 50 | 49 | 1 | 0 | 98
PRJ-001 | Sprint 5 | 2025-03-10 | 2025-03-21 | Completed | 55 | 53 | 52 | 1 | 0 | 98
PRJ-001 | Sprint 6 | 2025-03-24 | 2025-04-04 | Completed | 52 | 54 | 53 | 1 | 0 | 98
PRJ-001 | Sprint 7 | 2025-04-07 | 2025-04-18 | Completed | 58 | 56 | 55 | 1 | 0 | 98
PRJ-001 | Sprint 8 | 2025-04-21 | 2025-05-02 | Completed | 60 | 59 | 57 | 2 | 0 | 97
PRJ-001 | Sprint 9 | 2025-05-05 | 2025-05-16 | Completed | 55 | 57 | 55 | 2 | 0 | 96
PRJ-001 | Sprint 10 | 2025-05-19 | 2025-05-30 | Active | 60 | 40 | 38 | 2 | 0 | 95
PRJ-002 | Sprint 1 | 2025-02-03 | 2025-02-14 | Completed | 50 | 50 | 48 | 2 | 0 | 96
PRJ-002 | Sprint 2 | 2025-02-17 | 2025-02-28 | Completed | 55 | 52 | 50 | 2 | 0 | 96
PRJ-002 | Sprint 3 | 2025-03-03 | 2025-03-14 | Completed | 60 | 58 | 56 | 2 | 0 | 97
PRJ-002 | Sprint 4 | 2025-03-17 | 2025-03-28 | Completed | 65 | 60 | 56 | 4 | 0 | 93
PRJ-002 | Sprint 5 | 2025-03-31 | 2025-04-11 | Completed | 70 | 65 | 60 | 5 | 0 | 92
PRJ-002 | Sprint 6 | 2025-04-14 | 2025-04-25 | Completed | 68 | 70 | 65 | 5 | 0 | 93
PRJ-002 | Sprint 7 | 2025-04-28 | 2025-05-09 | Completed | 72 | 68 | 62 | 6 | 0 | 91
PRJ-002 | Sprint 8 | 2025-05-12 | 2025-05-23 | Active | 75 | 45 | 38 | 7 | 0 | 84
PRJ-006 | Sprint 1 | 2025-01-20 | 2025-01-31 | Completed | 80 | 80 | 78 | 2 | 0 | 98
PRJ-006 | Sprint 2 | 2025-02-03 | 2025-02-14 | Completed | 85 | 82 | 80 | 2 | 0 | 98
PRJ-006 | Sprint 3 | 2025-02-17 | 2025-02-28 | Completed | 90 | 88 | 85 | 3 | 0 | 97
PRJ-006 | Sprint 4 | 2025-03-03 | 2025-03-14 | Completed | 88 | 85 | 80 | 5 | 0 | 94
PRJ-006 | Sprint 5 | 2025-03-17 | 2025-03-28 | Completed | 92 | 90 | 85 | 5 | 0 | 94
PRJ-006 | Sprint 6 | 2025-03-31 | 2025-04-11 | Completed | 95 | 92 | 88 | 4 | 0 | 96
PRJ-006 | Sprint 7 | 2025-04-14 | 2025-04-25 | Completed | 98 | 95 | 90 | 5 | 0 | 95
PRJ-006 | Sprint 8 | 2025-04-28 | 2025-05-09 | Active | 100 | 60 | 55 | 5 | 0 | 92
PRJ-008 | Sprint 1 | 2025-02-17 | 2025-02-28 | Completed | 40 | 40 | 39 | 1 | 0 | 98
PRJ-008 | Sprint 2 | 2025-03-03 | 2025-03-14 | Completed | 45 | 44 | 42 | 2 | 0 | 95
PRJ-008 | Sprint 3 | 2025-03-17 | 2025-03-28 | Completed | 48 | 48 | 46 | 2 | 0 | 96
PRJ-008 | Sprint 4 | 2025-03-31 | 2025-04-11 | Completed | 50 | 50 | 48 | 2 | 0 | 96
PRJ-008 | Sprint 5 | 2025-04-14 | 2025-04-25 | Completed | 52 | 52 | 50 | 2 | 0 | 96
PRJ-008 | Sprint 6 | 2025-04-28 | 2025-05-09 | Active | 55 | 30 | 28 | 2 | 0 | 93

## Tasks
Task ID | Project ID | Sprint | Epic | Task Type | Description | Priority | Status | Assignee | Story Points | Cycle Time (days) | Lead Time (days) | Completed Date
TASK-0001 | PRJ-001 | Sprint 5 | EPIC-API | Bug | Task description for TASK-0001 | High | To Do | Aryan Chopra | 11
TASK-0002 | PRJ-001 | Sprint 7 | EPIC-Authentication | User Story | Task description for TASK-0002 | Critical | Done | Karan Patel | 2 | 9 | 5 | 2025-05-15
TASK-0003 | PRJ-001 | Sprint 4 | EPIC-Integration | Bug | Task description for TASK-0003 | Low | Done | Manish Dubey | 4 | 1 | 20 | 2025-05-15
TASK-0004 | PRJ-001 | Sprint 7 | EPIC-Data Pipeline | Technical Debt | Task description for TASK-0004 | High | Done | Karan Patel | 5 | 1 | 8 | 2025-05-15
TASK-0005 | PRJ-001 | Sprint 2 | EPIC-Integration | User Story | Task description for TASK-0005 | Medium | In Progress | Farhan Sheikh | 13
TASK-0006 | PRJ-001 | Sprint 1 | EPIC-Security | Sub-Task | Task description for TASK-0006 | Critical | In Progress | Tanvi Reddy | 10
TASK-0007 | PRJ-001 | Sprint 4 | EPIC-Dashboard | User Story | Task description for TASK-0007 | High | Done | Sonal Gupta | 2 | 14 | 14 | 2025-05-15
TASK-0008 | PRJ-001 | Sprint 7 | EPIC-UI/UX | Spike | Task description for TASK-0008 | Medium | Done | Divya Nair | 2 | 14 | 6 | 2025-05-15
TASK-0009 | PRJ-001 | Sprint 5 | EPIC-Dashboard | Sub-Task | Task description for TASK-0009 | High | In Progress | Pooja Iyer | 6
TASK-0010 | PRJ-001 | Sprint 8 | EPIC-Integration | Technical Debt | Task description for TASK-0010 | High | In Progress | Sneha Tiwari | 12
TASK-0011 | PRJ-001 | Sprint 4 | EPIC-Authentication | Technical Debt | Task description for TASK-0011 | Low | Done | Sonal Gupta | 6 | 13 | 4 | 2025-05-15
TASK-0012 | PRJ-001 | Sprint 6 | EPIC-API | Spike | Task description for TASK-0012 | Low | In Progress | Sneha Tiwari | 2
TASK-0013 | PRJ-001 | Sprint 3 | EPIC-API | Sub-Task | Task description for TASK-0013 | Medium | To Do | Aryan Chopra | 8
TASK-0014 | PRJ-001 | Sprint 7 | EPIC-Data Pipeline | Bug | Task description for TASK-0014 | High | In Progress | Pooja Iyer | 10
TASK-0015 | PRJ-001 | Sprint 1 | EPIC-Dashboard | Bug | Task description for TASK-0015 | High | To Do | Sneha Tiwari | 8
TASK-0016 | PRJ-001 | Sprint 8 | EPIC-UI/UX | Sub-Task | Task description for TASK-0016 | Critical | Done | Sneha Tiwari | 7 | 7 | 15 | 2025-05-15
TASK-0017 | PRJ-001 | Sprint 5 | EPIC-Data Pipeline | User Story | Task description for TASK-0017 | Medium | To Do | Tanvi Reddy | 12
TASK-0018 | PRJ-001 | Sprint 5 | EPIC-Reporting | Sub-Task | Task description for TASK-0018 | Critical | In Progress | Sneha Tiwari | 3
TASK-0019 | PRJ-001 | Sprint 3 | EPIC-Data Pipeline | Bug | Task description for TASK-0019 | Critical | Done | Manish Dubey | 5 | 9 | 9 | 2025-05-15
TASK-0020 | PRJ-001 | Sprint 2 | EPIC-Data Pipeline | Technical Debt | Task description for TASK-0020 | High | In Progress | Ayesha Malik | 6
TASK-0021 | PRJ-001 | Sprint 8 | EPIC-Dashboard | Sub-Task | Task description for TASK-0021 | High | Done | Divya Nair | 4 | 2 | 5 | 2025-05-15
TASK-0022 | PRJ-001 | Sprint 3 | EPIC-UI/UX | Sub-Task | Task description for TASK-0022 | Low | In Progress | Karan Patel | 11
TASK-0023 | PRJ-001 | Sprint 5 | EPIC-Integration | Technical Debt | Task description for TASK-0023 | Low | Done | Pooja Iyer | 9 | 12 | 9 | 2025-05-15
TASK-0024 | PRJ-001 | Sprint 4 | EPIC-Dashboard | Technical Debt | Task description for TASK-0024 | Critical | To Do | Manish Dubey | 8
TASK-0025 | PRJ-001 | Sprint 4 | EPIC-Authentication | User Story | Task description for TASK-0025 | Critical | In Progress | Karan Patel | 9
TASK-0026 | PRJ-001 | Sprint 6 | EPIC-Dashboard | Sub-Task | Task description for TASK-0026 | High | Blocked | Sonal Gupta | 2
TASK-0027 | PRJ-001 | Sprint 3 | EPIC-Security | Bug | Task description for TASK-0027 | Low | In Progress | Tanvi Reddy | 11
TASK-0028 | PRJ-001 | Sprint 7 | EPIC-Data Pipeline | Spike | Task description for TASK-0028 | Low | To Do | Nikhil Rao | 4
TASK-0029 | PRJ-001 | Sprint 2 | EPIC-Authentication | Spike | Task description for TASK-0029 | Medium | To Do | Rohan Joshi | 12
TASK-0030 | PRJ-001 | Sprint 8 | EPIC-Reporting | Spike | Task description for TASK-0030 | High | To Do | Sonal Gupta | 4
TASK-0031 | PRJ-001 | Sprint 2 | EPIC-Security | Sub-Task | Task description for TASK-0031 | Critical | In Progress | Ayesha Malik | 8
TASK-0032 | PRJ-001 | Sprint 1 | EPIC-Dashboard | Bug | Task description for TASK-0032 | High | Blocked | Tanvi Reddy | 11
TASK-0033 | PRJ-001 | Sprint 7 | EPIC-Authentication | Bug | Task description for TASK-0033 | Low | In Progress | Ayesha Malik | 8
TASK-0034 | PRJ-001 | Sprint 8 | EPIC-UI/UX | Spike | Task description for TASK-0034 | Low | In Progress | Divya Nair | 7
TASK-0035 | PRJ-001 | Sprint 1 | EPIC-Authentication | Technical Debt | Task description for TASK-0035 | Critical | In Progress | Ayesha Malik | 4
TASK-0036 | PRJ-001 | Sprint 3 | EPIC-Authentication | Sub-Task | Task description for TASK-0036 | Critical | In Progress | Divya Nair | 10
TASK-0037 | PRJ-001 | Sprint 7 | EPIC-Dashboard | Sub-Task | Task description for TASK-0037 | High | Done | Manish Dubey | 2 | 11 | 10 | 2025-05-15
TASK-0038 | PRJ-001 | Sprint 2 | EPIC-Integration | Sub-Task | Task description for TASK-0038 | Medium | To Do | Sonal Gupta | 10
TASK-0039 | PRJ-001 | Sprint 5 | EPIC-Integration | Bug | Task description for TASK-0039 | Medium | Done | Nikhil Rao | 4 | 6 | 10 | 2025-05-15
TASK-0040 | PRJ-001 | Sprint 2 | EPIC-Authentication | Spike | Task description for TASK-0040 | Critical | Blocked | Rohan Joshi | 6
TASK-0041 | PRJ-002 | Sprint 5 | EPIC-Reporting | Technical Debt | Task description for TASK-0041 | Critical | In Progress | Karan Patel | 9
TASK-0042 | PRJ-002 | Sprint 8 | EPIC-UI/UX | Sub-Task | Task description for TASK-0042 | Critical | In Progress | Sneha Tiwari | 6
TASK-0043 | PRJ-002 | Sprint 2 | EPIC-Reporting | Technical Debt | Task description for TASK-0043 | Critical | In Progress | Rohan Joshi | 9
TASK-0044 | PRJ-002 | Sprint 4 | EPIC-Data Pipeline | Bug | Task description for TASK-0044 | Medium | Done | Pooja Iyer | 12 | 5 | 12 | 2025-05-15
TASK-0045 | PRJ-002 | Sprint 1 | EPIC-Dashboard | Spike | Task description for TASK-0045 | Medium | In Progress | Ayesha Malik | 8
TASK-0046 | PRJ-002 | Sprint 3 | EPIC-UI/UX | Bug | Task description for TASK-0046 | Low | In Progress | Pooja Iyer | 1
TASK-0047 | PRJ-002 | Sprint 1 | EPIC-Dashboard | User Story | Task description for TASK-0047 | High | In Progress | Pooja Iyer | 12
TASK-0048 | PRJ-002 | Sprint 3 | EPIC-Integration | Bug | Task description for TASK-0048 | Critical | Done | Sonal Gupta | 1 | 10 | 20 | 2025-05-15
TASK-0049 | PRJ-002 | Sprint 6 | EPIC-API | Bug | Task description for TASK-0049 | Critical | Done | Farhan Sheikh | 6 | 13 | 4 | 2025-05-15
TASK-0050 | PRJ-002 | Sprint 3 | EPIC-API | Bug | Task description for TASK-0050 | High | Done | Tanvi Reddy | 13 | 14 | 16 | 2025-05-15
TASK-0051 | PRJ-002 | Sprint 6 | EPIC-Integration | Bug | Task description for TASK-0051 | Medium | To Do | Divya Nair | 1
TASK-0052 | PRJ-002 | Sprint 8 | EPIC-API | Bug | Task description for TASK-0052 | Low | Done | Farhan Sheikh | 13 | 7 | 4 | 2025-05-15
TASK-0053 | PRJ-002 | Sprint 4 | EPIC-Authentication | Bug | Task description for TASK-0053 | Low | Done | Farhan Sheikh | 5 | 14 | 10 | 2025-05-15
TASK-0054 | PRJ-002 | Sprint 6 | EPIC-Integration | Sub-Task | Task description for TASK-0054 | Medium | Done | Ayesha Malik | 5 | 13 | 11 | 2025-05-15
TASK-0055 | PRJ-002 | Sprint 5 | EPIC-Authentication | User Story | Task description for TASK-0055 | Low | Done | Farhan Sheikh | 2 | 5 | 8 | 2025-05-15
TASK-0056 | PRJ-002 | Sprint 2 | EPIC-Integration | Sub-Task | Task description for TASK-0056 | High | Done | Sonal Gupta | 12 | 7 | 19 | 2025-05-15
TASK-0057 | PRJ-002 | Sprint 4 | EPIC-Data Pipeline | Spike | Task description for TASK-0057 | Critical | Done | Sneha Tiwari | 1 | 1 | 19 | 2025-05-15
TASK-0058 | PRJ-002 | Sprint 5 | EPIC-UI/UX | Spike | Task description for TASK-0058 | Medium | Done | Tanvi Reddy | 6 | 11 | 6 | 2025-05-15
TASK-0059 | PRJ-002 | Sprint 3 | EPIC-API | Spike | Task description for TASK-0059 | Low | In Progress | Sneha Tiwari | 12
TASK-0060 | PRJ-002 | Sprint 5 | EPIC-Integration | Sub-Task | Task description for TASK-0060 | Critical | Blocked | Sonal Gupta | 12
TASK-0061 | PRJ-002 | Sprint 6 | EPIC-Security | Spike | Task description for TASK-0061 | Low | In Progress | Sneha Tiwari | 5
TASK-0062 | PRJ-002 | Sprint 2 | EPIC-UI/UX | Sub-Task | Task description for TASK-0062 | Medium | Done | Rohan Joshi | 4 | 13 | 8 | 2025-05-15
TASK-0063 | PRJ-002 | Sprint 5 | EPIC-API | Bug | Task description for TASK-0063 | High | In Progress | Ayesha Malik | 13
TASK-0064 | PRJ-002 | Sprint 8 | EPIC-Dashboard | Spike | Task description for TASK-0064 | Low | In Progress | Sneha Tiwari | 1
TASK-0065 | PRJ-002 | Sprint 7 | EPIC-Security | Spike | Task description for TASK-0065 | High | To Do | Divya Nair | 10
TASK-0066 | PRJ-002 | Sprint 7 | EPIC-API | Bug | Task description for TASK-0066 | Low | Done | Ayesha Malik | 11 | 13 | 6 | 2025-05-15
TASK-0067 | PRJ-002 | Sprint 2 | EPIC-Security | Bug | Task description for TASK-0067 | Low | In Progress | Sneha Tiwari | 9
TASK-0068 | PRJ-002 | Sprint 6 | EPIC-Security | Sub-Task | Task description for TASK-0068 | Low | Blocked | Pooja Iyer | 9
TASK-0069 | PRJ-002 | Sprint 8 | EPIC-UI/UX | Bug | Task description for TASK-0069 | Medium | Done | Pooja Iyer | 8 | 12 | 18 | 2025-05-15
TASK-0070 | PRJ-002 | Sprint 2 | EPIC-UI/UX | Bug | Task description for TASK-0070 | Medium | Done | Farhan Sheikh | 8 | 5 | 17 | 2025-05-15
TASK-0071 | PRJ-002 | Sprint 3 | EPIC-API | Spike | Task description for TASK-0071 | High | Done | Aryan Chopra | 6 | 2 | 7 | 2025-05-15
TASK-0072 | PRJ-002 | Sprint 7 | EPIC-Data Pipeline | Sub-Task | Task description for TASK-0072 | Low | To Do | Tanvi Reddy | 4
TASK-0073 | PRJ-002 | Sprint 7 | EPIC-Integration | Sub-Task | Task description for TASK-0073 | Critical | In Progress | Manish Dubey | 1
TASK-0074 | PRJ-002 | Sprint 6 | EPIC-UI/UX | Spike | Task description for TASK-0074 | Low | In Progress | Pooja Iyer | 7
TASK-0075 | PRJ-002 | Sprint 8 | EPIC-API | Technical Debt | Task description for TASK-0075 | Low | Done | Nikhil Rao | 12 | 13 | 10 | 2025-05-15
TASK-0076 | PRJ-002 | Sprint 7 | EPIC-Reporting | Spike | Task description for TASK-0076 | High | In Progress | Manish Dubey | 1
TASK-0077 | PRJ-002 | Sprint 7 | EPIC-Authentication | User Story | Task description for TASK-0077 | Low | To Do | Divya Nair | 9
TASK-0078 | PRJ-002 | Sprint 5 | EPIC-Integration | Technical Debt | Task description for TASK-0078 | High | To Do | Nikhil Rao | 8
TASK-0079 | PRJ-002 | Sprint 7 | EPIC-UI/UX | Spike | Task description for TASK-0079 | Medium | In Progress | Rohan Joshi | 6
TASK-0080 | PRJ-002 | Sprint 1 | EPIC-Data Pipeline | Bug | Task description for TASK-0080 | Critical | To Do | Sneha Tiwari | 8
TASK-0081 | PRJ-006 | Sprint 1 | EPIC-Reporting | Bug | Task description for TASK-0081 | High | Done | Nikhil Rao | 1 | 4 | 9 | 2025-05-15
TASK-0082 | PRJ-006 | Sprint 4 | EPIC-Security | Technical Debt | Task description for TASK-0082 | Medium | To Do | Divya Nair | 11
TASK-0083 | PRJ-006 | Sprint 3 | EPIC-UI/UX | User Story | Task description for TASK-0083 | Critical | Done | Sonal Gupta | 10 | 12 | 6 | 2025-05-15
TASK-0084 | PRJ-006 | Sprint 4 | EPIC-Dashboard | Sub-Task | Task description for TASK-0084 | High | Done | Rohan Joshi | 10 | 7 | 15 | 2025-05-15
TASK-0085 | PRJ-006 | Sprint 1 | EPIC-Data Pipeline | Sub-Task | Task description for TASK-0085 | Low | Done | Sneha Tiwari | 12 | 14 | 6 | 2025-05-15
TASK-0086 | PRJ-006 | Sprint 6 | EPIC-Authentication | Spike | Task description for TASK-0086 | Low | To Do | Rohan Joshi | 6
TASK-0087 | PRJ-006 | Sprint 8 | EPIC-Reporting | Spike | Task description for TASK-0087 | High | Blocked | Aryan Chopra | 7
TASK-0088 | PRJ-006 | Sprint 5 | EPIC-Security | Spike | Task description for TASK-0088 | Low | Blocked | Aryan Chopra | 9
TASK-0089 | PRJ-006 | Sprint 4 | EPIC-Dashboard | Technical Debt | Task description for TASK-0089 | Low | In Progress | Karan Patel | 10
TASK-0090 | PRJ-006 | Sprint 7 | EPIC-Data Pipeline | User Story | Task description for TASK-0090 | Low | In Progress | Farhan Sheikh | 13
TASK-0091 | PRJ-006 | Sprint 6 | EPIC-UI/UX | Technical Debt | Task description for TASK-0091 | Medium | In Progress | Manish Dubey | 3
TASK-0092 | PRJ-006 | Sprint 4 | EPIC-Dashboard | Bug | Task description for TASK-0092 | Low | Done | Nikhil Rao | 12 | 9 | 3 | 2025-05-15
TASK-0093 | PRJ-006 | Sprint 8 | EPIC-Security | User Story | Task description for TASK-0093 | Critical | Done | Sonal Gupta | 9 | 12 | 18 | 2025-05-15
TASK-0094 | PRJ-006 | Sprint 4 | EPIC-UI/UX | Sub-Task | Task description for TASK-0094 | Medium | In Progress | Nikhil Rao | 4
TASK-0095 | PRJ-006 | Sprint 6 | EPIC-Data Pipeline | Spike | Task description for TASK-0095 | Medium | Done | Sonal Gupta | 9 | 7 | 20 | 2025-05-15
TASK-0096 | PRJ-006 | Sprint 4 | EPIC-Data Pipeline | User Story | Task description for TASK-0096 | High | In Progress | Karan Patel | 5
TASK-0097 | PRJ-006 | Sprint 5 | EPIC-Dashboard | Bug | Task description for TASK-0097 | Medium | Done | Karan Patel | 4 | 5 | 21 | 2025-05-15
TASK-0098 | PRJ-006 | Sprint 1 | EPIC-Reporting | Technical Debt | Task description for TASK-0098 | Critical | To Do | Ayesha Malik | 6
TASK-0099 | PRJ-006 | Sprint 3 | EPIC-Security | User Story | Task description for TASK-0099 | Critical | In Progress | Manish Dubey | 9
TASK-0100 | PRJ-006 | Sprint 8 | EPIC-Data Pipeline | Bug | Task description for TASK-0100 | Critical | In Progress | Sonal Gupta | 5
TASK-0101 | PRJ-006 | Sprint 2 | EPIC-Integration | Spike | Task description for TASK-0101 | Critical | To Do | Manish Dubey | 8
TASK-0102 | PRJ-006 | Sprint 5 | EPIC-Dashboard | Bug | Task description for TASK-0102 | Critical | Done | Pooja Iyer | 11 | 3 | 7 | 2025-05-15
TASK-0103 | PRJ-006 | Sprint 4 | EPIC-Integration | Spike | Task description for TASK-0103 | Low | In Progress | Sonal Gupta | 13
TASK-0104 | PRJ-006 | Sprint 5 | EPIC-Authentication | Sub-Task | Task description for TASK-0104 | Critical | Blocked | Karan Patel | 10
TASK-0105 | PRJ-006 | Sprint 2 | EPIC-Reporting | Bug | Task description for TASK-0105 | High | In Progress | Pooja Iyer | 11
TASK-0106 | PRJ-006 | Sprint 7 | EPIC-Security | Sub-Task | Task description for TASK-0106 | Low | To Do | Sonal Gupta | 2
TASK-0107 | PRJ-006 | Sprint 5 | EPIC-Security | User Story | Task description for TASK-0107 | High | In Progress | Sonal Gupta | 1
TASK-0108 | PRJ-006 | Sprint 7 | EPIC-Dashboard | Sub-Task | Task description for TASK-0108 | High | Done | Sneha Tiwari | 13 | 10 | 9 | 2025-05-15
TASK-0109 | PRJ-006 | Sprint 3 | EPIC-Dashboard | User Story | Task description for TASK-0109 | High | Blocked | Sonal Gupta | 3
TASK-0110 | PRJ-006 | Sprint 8 | EPIC-Dashboard | Spike | Task description for TASK-0110 | Medium | Done | Aryan Chopra | 10 | 10 | 12 | 2025-05-15
TASK-0111 | PRJ-006 | Sprint 8 | EPIC-Security | User Story | Task description for TASK-0111 | Critical | Blocked | Tanvi Reddy | 7
TASK-0112 | PRJ-006 | Sprint 5 | EPIC-Authentication | User Story | Task description for TASK-0112 | High | In Progress | Sneha Tiwari | 12
TASK-0113 | PRJ-006 | Sprint 1 | EPIC-Reporting | Spike | Task description for TASK-0113 | Low | Done | Sonal Gupta | 10 | 1 | 11 | 2025-05-15
TASK-0114 | PRJ-006 | Sprint 7 | EPIC-Security | User Story | Task description for TASK-0114 | Low | Blocked | Farhan Sheikh | 3
TASK-0115 | PRJ-006 | Sprint 2 | EPIC-Reporting | Technical Debt | Task description for TASK-0115 | Low | In Progress | Aryan Chopra | 7
TASK-0116 | PRJ-006 | Sprint 7 | EPIC-Authentication | Spike | Task description for TASK-0116 | Critical | In Progress | Farhan Sheikh | 8
TASK-0117 | PRJ-006 | Sprint 7 | EPIC-Authentication | Sub-Task | Task description for TASK-0117 | Low | In Progress | Tanvi Reddy | 5
TASK-0118 | PRJ-006 | Sprint 6 | EPIC-Security | Spike | Task description for TASK-0118 | Critical | To Do | Karan Patel | 1
TASK-0119 | PRJ-006 | Sprint 8 | EPIC-Dashboard | User Story | Task description for TASK-0119 | High | Done | Aryan Chopra | 5 | 5 | 17 | 2025-05-15
TASK-0120 | PRJ-006 | Sprint 1 | EPIC-Integration | User Story | Task description for TASK-0120 | High | In Progress | Rohan Joshi | 3
TASK-0121 | PRJ-008 | Sprint 3 | EPIC-Security | Technical Debt | Task description for TASK-0121 | Medium | Blocked | Tanvi Reddy | 8
TASK-0122 | PRJ-008 | Sprint 4 | EPIC-Security | Sub-Task | Task description for TASK-0122 | High | Blocked | Tanvi Reddy | 8
TASK-0123 | PRJ-008 | Sprint 3 | EPIC-Dashboard | Technical Debt | Task description for TASK-0123 | Low | Blocked | Farhan Sheikh | 4
TASK-0124 | PRJ-008 | Sprint 5 | EPIC-UI/UX | Sub-Task | Task description for TASK-0124 | Low | Done | Divya Nair | 13 | 14 | 3 | 2025-05-15
TASK-0125 | PRJ-008 | Sprint 7 | EPIC-Security | Technical Debt | Task description for TASK-0125 | High | Done | Aryan Chopra | 8 | 6 | 13 | 2025-05-15
TASK-0126 | PRJ-008 | Sprint 1 | EPIC-Data Pipeline | Spike | Task description for TASK-0126 | Low | Done | Tanvi Reddy | 4 | 4 | 16 | 2025-05-15
TASK-0127 | PRJ-008 | Sprint 8 | EPIC-Authentication | Bug | Task description for TASK-0127 | Medium | Done | Rohan Joshi | 11 | 11 | 7 | 2025-05-15
TASK-0128 | PRJ-008 | Sprint 8 | EPIC-Authentication | Bug | Task description for TASK-0128 | Low | To Do | Sneha Tiwari | 8
TASK-0129 | PRJ-008 | Sprint 5 | EPIC-Data Pipeline | Sub-Task | Task description for TASK-0129 | Low | To Do | Sneha Tiwari | 3
TASK-0130 | PRJ-008 | Sprint 7 | EPIC-Data Pipeline | Spike | Task description for TASK-0130 | Critical | Done | Manish Dubey | 2 | 14 | 20 | 2025-05-15
TASK-0131 | PRJ-008 | Sprint 5 | EPIC-API | User Story | Task description for TASK-0131 | Low | In Progress | Rohan Joshi | 2
TASK-0132 | PRJ-008 | Sprint 8 | EPIC-Reporting | Technical Debt | Task description for TASK-0132 | Critical | Done | Ayesha Malik | 13 | 14 | 6 | 2025-05-15
TASK-0133 | PRJ-008 | Sprint 6 | EPIC-Integration | Bug | Task description for TASK-0133 | High | Done | Pooja Iyer | 6 | 5 | 14 | 2025-05-15
TASK-0134 | PRJ-008 | Sprint 3 | EPIC-Reporting | User Story | Task description for TASK-0134 | Low | Done | Manish Dubey | 7 | 13 | 8 | 2025-05-15
TASK-0135 | PRJ-008 | Sprint 3 | EPIC-API | Spike | Task description for TASK-0135 | Medium | In Progress | Nikhil Rao | 11
TASK-0136 | PRJ-008 | Sprint 5 | EPIC-Reporting | User Story | Task description for TASK-0136 | Low | Done | Farhan Sheikh | 5 | 13 | 17 | 2025-05-15
TASK-0137 | PRJ-008 | Sprint 7 | EPIC-UI/UX | Spike | Task description for TASK-0137 | Medium | In Progress | Karan Patel | 10
TASK-0138 | PRJ-008 | Sprint 7 | EPIC-Data Pipeline | Sub-Task | Task description for TASK-0138 | Medium | Done | Aryan Chopra | 7 | 2 | 10 | 2025-05-15
TASK-0139 | PRJ-008 | Sprint 7 | EPIC-UI/UX | User Story | Task description for TASK-0139 | Critical | To Do | Manish Dubey | 5
TASK-0140 | PRJ-008 | Sprint 5 | EPIC-API | Sub-Task | Task description for TASK-0140 | Medium | In Progress | Karan Patel | 12
TASK-0141 | PRJ-008 | Sprint 5 | EPIC-Reporting | User Story | Task description for TASK-0141 | Critical | To Do | Sonal Gupta | 11
TASK-0142 | PRJ-008 | Sprint 6 | EPIC-Reporting | User Story | Task description for TASK-0142 | Medium | In Progress | Farhan Sheikh | 13
TASK-0143 | PRJ-008 | Sprint 4 | EPIC-Reporting | Sub-Task | Task description for TASK-0143 | Medium | In Progress | Pooja Iyer | 12
TASK-0144 | PRJ-008 | Sprint 3 | EPIC-UI/UX | Spike | Task description for TASK-0144 | Medium | Blocked | Aryan Chopra | 9
TASK-0145 | PRJ-008 | Sprint 3 | EPIC-API | Spike | Task description for TASK-0145 | Medium | Done | Rohan Joshi | 6 | 8 | 5 | 2025-05-15
TASK-0146 | PRJ-008 | Sprint 5 | EPIC-Dashboard | Spike | Task description for TASK-0146 | Medium | In Progress | Sneha Tiwari | 13
TASK-0147 | PRJ-008 | Sprint 6 | EPIC-Dashboard | Bug | Task description for TASK-0147 | Low | Done | Ayesha Malik | 12 | 10 | 15 | 2025-05-15
TASK-0148 | PRJ-008 | Sprint 4 | EPIC-Dashboard | Spike | Task description for TASK-0148 | Medium | Done | Sneha Tiwari | 10 | 9 | 13 | 2025-05-15
TASK-0149 | PRJ-008 | Sprint 1 | EPIC-Authentication | Technical Debt | Task description for TASK-0149 | Low | To Do | Rohan Joshi | 7
TASK-0150 | PRJ-008 | Sprint 3 | EPIC-Integration | Spike | Task description for TASK-0150 | Medium | In Progress | Sneha Tiwari | 2
TASK-0151 | PRJ-008 | Sprint 3 | EPIC-Integration | User Story | Task description for TASK-0151 | Low | Done | Manish Dubey | 12 | 9 | 16 | 2025-05-15
TASK-0152 | PRJ-008 | Sprint 5 | EPIC-Authentication | Technical Debt | Task description for TASK-0152 | High | Blocked | Nikhil Rao | 7
TASK-0153 | PRJ-008 | Sprint 6 | EPIC-Dashboard | Technical Debt | Task description for TASK-0153 | Medium | Blocked | Ayesha Malik | 8
TASK-0154 | PRJ-008 | Sprint 2 | EPIC-Security | User Story | Task description for TASK-0154 | High | In Progress | Sneha Tiwari | 7
TASK-0155 | PRJ-008 | Sprint 6 | EPIC-API | Bug | Task description for TASK-0155 | High | Done | Rohan Joshi | 11 | 1 | 4 | 2025-05-15
TASK-0156 | PRJ-008 | Sprint 4 | EPIC-Data Pipeline | Bug | Task description for TASK-0156 | Critical | Done | Sonal Gupta | 13 | 10 | 9 | 2025-05-15
TASK-0157 | PRJ-008 | Sprint 5 | EPIC-Reporting | User Story | Task description for TASK-0157 | Critical | Blocked | Divya Nair | 3
TASK-0158 | PRJ-008 | Sprint 4 | EPIC-Data Pipeline | User Story | Task description for TASK-0158 | High | In Progress | Sonal Gupta | 1
TASK-0159 | PRJ-008 | Sprint 7 | EPIC-Dashboard | User Story | Task description for TASK-0159 | Low | To Do | Nikhil Rao | 1
TASK-0160 | PRJ-008 | Sprint 2 | EPIC-Security | Sub-Task | Task description for TASK-0160 | High | In Progress | Manish Dubey | 13

## Risks_Issues
Risk ID | Project ID | Type | Description | Likelihood | Impact | Severity | Status | Owner | Identified Date | Mitigation Plan | Target Resolution
RISK-001 | PRJ-001 | Risk | Third-party API deprecation | High | High | Critical | Open | Raj Mehta | 2025-04-01 | Identify alternative API providers | 2025-06-30
RISK-002 | PRJ-002 | Risk | Regulatory compliance gap | Critical | High | Critical | Open | Neha Sharma | 2025-03-15 | Engage legal team for compliance review | 2025-06-15
RISK-003 | PRJ-001 | Issue | UAT environment instability | Medium | Medium | High | In Progress | Priya Singh | 2025-04-20 | Provision dedicated UAT infra | 2025-05-30
RISK-004 | PRJ-004 | Risk | Data migration data loss | High | Critical | Critical | Open | Amit Verma | 2025-03-01 | Implement full backup strategy | 2025-07-01
RISK-005 | PRJ-006 | Issue | Model hallucination rate >5% | High | High | Critical | In Progress | Vikram Nair | 2025-04-05 | Fine-tune on domain-specific dataset | 2025-06-20
RISK-006 | PRJ-002 | Issue | Payment gateway timeout | Critical | High | Critical | Escalated | Sarah Khan | 2025-05-01 | Implement retry logic and circuit breaker | 2025-05-25
RISK-007 | PRJ-008 | Risk | Scope creep from stakeholders | Medium | Low | Medium | Open | Arjun Das | 2025-04-10 | Formal change request process | 2025-12-31
RISK-008 | PRJ-001 | Risk | Key resource leaving team | Low | Medium | Medium | Mitigated | Sarah Khan | 2025-02-01 | Cross-training completed | 2025-03-15
RISK-009 | PRJ-006 | Risk | Infrastructure cost overrun | High | Medium | High | Open | Vikram Nair | 2025-05-10 | Monthly cost reviews with finance | 2025-08-31
RISK-010 | PRJ-004 | Issue | Legacy system incompatibility | Critical | Critical | Critical | In Progress | Amit Verma | 2025-04-15 | Build adapter layer | 2025-07-15
RISK-011 | PRJ-005 | Risk | Vendor delivery delay | Medium | Medium | High | Open | Neha Sharma | 2025-05-20 | Parallel vendor evaluation | 2025-09-30
RISK-012 | PRJ-002 | Risk | Security vulnerability in auth | High | Critical | Critical | In Progress | Raj Mehta | 2025-05-12 | Penetration testing underway | 2025-06-10

## Team_Capacity
Team Member | Role | Project ID | Sprint | Available Hours | Logged Hours | Utilization % | Tasks Completed | Story Points Delivered | Avg Cycle Time (days) | Skill Level
Ayesha Malik | Sr. Developer | PRJ-008 | Sprint 1 | 78 | 66 | 84.6 | 7 | 13 | 3.4 | Mid
Ayesha Malik | Sr. Developer | PRJ-008 | Sprint 2 | 73 | 64 | 87.7 | 8 | 20 | 5.2 | Junior
Ayesha Malik | Sr. Developer | PRJ-008 | Sprint 3 | 79 | 66 | 83.5 | 6 | 14 | 6.8 | Senior
Ayesha Malik | Sr. Developer | PRJ-008 | Sprint 4 | 78 | 66 | 84.6 | 4 | 22 | 6 | Senior
Ayesha Malik | Sr. Developer | PRJ-008 | Sprint 5 | 73 | 71 | 97.3 | 7 | 10 | 4.8 | Lead
Ayesha Malik | Sr. Developer | PRJ-008 | Sprint 6 | 72 | 64 | 88.9 | 7 | 8 | 4.6 | Senior
Ayesha Malik | Sr. Developer | PRJ-008 | Sprint 7 | 80 | 62 | 77.5 | 6 | 24 | 7.4 | Lead
Ayesha Malik | Sr. Developer | PRJ-008 | Sprint 8 | 72 | 65 | 90.3 | 4 | 14 | 7.7 | Mid
Rohan Joshi | Business Analyst | PRJ-008 | Sprint 1 | 74 | 68 | 91.9 | 8 | 13 | 2.2 | Junior
Rohan Joshi | Business Analyst | PRJ-008 | Sprint 2 | 74 | 67 | 90.5 | 8 | 21 | 2.5 | Lead
Rohan Joshi | Business Analyst | PRJ-008 | Sprint 3 | 73 | 62 | 84.9 | 5 | 8 | 4.3 | Mid
Rohan Joshi | Business Analyst | PRJ-008 | Sprint 4 | 80 | 72 | 90 | 4 | 9 | 5.8 | Lead
Rohan Joshi | Business Analyst | PRJ-008 | Sprint 5 | 76 | 72 | 94.7 | 4 | 19 | 7.6 | Lead
Rohan Joshi | Business Analyst | PRJ-008 | Sprint 6 | 72 | 62 | 86.1 | 8 | 12 | 5.6 | Lead
Rohan Joshi | Business Analyst | PRJ-008 | Sprint 7 | 73 | 61 | 83.6 | 3 | 12 | 3.8 | Mid
Rohan Joshi | Business Analyst | PRJ-008 | Sprint 8 | 78 | 64 | 82.1 | 4 | 25 | 3.9 | Lead
Divya Nair | QA Engineer | PRJ-002 | Sprint 1 | 76 | 63 | 82.9 | 5 | 13 | 6.1 | Senior
Divya Nair | QA Engineer | PRJ-002 | Sprint 2 | 72 | 69 | 95.8 | 3 | 18 | 3.3 | Lead
Divya Nair | QA Engineer | PRJ-002 | Sprint 3 | 77 | 72 | 93.5 | 6 | 21 | 6.9 | Junior
Divya Nair | QA Engineer | PRJ-002 | Sprint 4 | 74 | 74 | 100 | 3 | 19 | 6.3 | Lead
Divya Nair | QA Engineer | PRJ-002 | Sprint 5 | 79 | 67 | 84.8 | 5 | 15 | 5.9 | Senior
Divya Nair | QA Engineer | PRJ-002 | Sprint 6 | 73 | 73 | 100 | 8 | 18 | 3.3 | Mid
Divya Nair | QA Engineer | PRJ-002 | Sprint 7 | 78 | 69 | 88.5 | 6 | 10 | 7.3 | Lead
Divya Nair | QA Engineer | PRJ-002 | Sprint 8 | 76 | 62 | 81.6 | 7 | 17 | 7.4 | Senior
Karan Patel | UI/UX Designer | PRJ-008 | Sprint 1 | 80 | 64 | 80 | 5 | 21 | 7.3 | Lead
Karan Patel | UI/UX Designer | PRJ-008 | Sprint 2 | 74 | 64 | 86.5 | 6 | 22 | 3.2 | Senior
Karan Patel | UI/UX Designer | PRJ-008 | Sprint 3 | 75 | 71 | 94.7 | 3 | 19 | 6.2 | Mid
Karan Patel | UI/UX Designer | PRJ-008 | Sprint 4 | 74 | 72 | 97.3 | 8 | 16 | 5.9 | Mid
Karan Patel | UI/UX Designer | PRJ-008 | Sprint 5 | 78 | 71 | 91 | 8 | 20 | 2 | Mid
Karan Patel | UI/UX Designer | PRJ-008 | Sprint 6 | 72 | 68 | 94.4 | 5 | 13 | 5.1 | Lead
Karan Patel | UI/UX Designer | PRJ-008 | Sprint 7 | 75 | 68 | 90.7 | 8 | 21 | 4.8 | Senior
Karan Patel | UI/UX Designer | PRJ-008 | Sprint 8 | 75 | 60 | 80 | 3 | 17 | 2.5 | Junior
Sonal Gupta | Developer | PRJ-001 | Sprint 1 | 78 | 69 | 88.5 | 5 | 25 | 5.8 | Senior
Sonal Gupta | Developer | PRJ-001 | Sprint 2 | 75 | 63 | 84 | 6 | 20 | 6.7 | Senior
Sonal Gupta | Developer | PRJ-001 | Sprint 3 | 79 | 70 | 88.6 | 4 | 12 | 7.4 | Lead
Sonal Gupta | Developer | PRJ-001 | Sprint 4 | 78 | 77 | 98.7 | 8 | 13 | 4.2 | Mid
Sonal Gupta | Developer | PRJ-001 | Sprint 5 | 76 | 74 | 97.4 | 7 | 20 | 3.1 | Lead
Sonal Gupta | Developer | PRJ-001 | Sprint 6 | 79 | 65 | 82.3 | 3 | 25 | 3.4 | Lead
Sonal Gupta | Developer | PRJ-001 | Sprint 7 | 80 | 60 | 75 | 3 | 18 | 6.8 | Junior
Sonal Gupta | Developer | PRJ-001 | Sprint 8 | 77 | 60 | 77.9 | 7 | 25 | 3.7 | Junior
Farhan Sheikh | Sr. Developer | PRJ-006 | Sprint 1 | 78 | 68 | 87.2 | 4 | 12 | 5.5 | Junior
Farhan Sheikh | Sr. Developer | PRJ-006 | Sprint 2 | 78 | 61 | 78.2 | 3 | 18 | 5.1 | Senior
Farhan Sheikh | Sr. Developer | PRJ-006 | Sprint 3 | 74 | 73 | 98.6 | 6 | 9 | 6.2 | Lead
Farhan Sheikh | Sr. Developer | PRJ-006 | Sprint 4 | 75 | 66 | 88 | 3 | 23 | 3 | Senior
Farhan Sheikh | Sr. Developer | PRJ-006 | Sprint 5 | 77 | 62 | 80.5 | 7 | 14 | 6.7 | Mid
Farhan Sheikh | Sr. Developer | PRJ-006 | Sprint 6 | 77 | 77 | 100 | 3 | 11 | 6.3 | Mid
Farhan Sheikh | Sr. Developer | PRJ-006 | Sprint 7 | 74 | 68 | 91.9 | 3 | 9 | 6.6 | Lead
Farhan Sheikh | Sr. Developer | PRJ-006 | Sprint 8 | 74 | 65 | 87.8 | 8 | 15 | 5.7 | Mid
Tanvi Reddy | Scrum Master | PRJ-006 | Sprint 1 | 72 | 65 | 90.3 | 8 | 21 | 3.1 | Mid
Tanvi Reddy | Scrum Master | PRJ-006 | Sprint 2 | 73 | 62 | 84.9 | 6 | 24 | 6.4 | Junior
Tanvi Reddy | Scrum Master | PRJ-006 | Sprint 3 | 75 | 72 | 96 | 8 | 11 | 6.7 | Mid
Tanvi Reddy | Scrum Master | PRJ-006 | Sprint 4 | 79 | 79 | 100 | 3 | 13 | 7.3 | Mid
Tanvi Reddy | Scrum Master | PRJ-006 | Sprint 5 | 79 | 71 | 89.9 | 5 | 18 | 5.5 | Lead
Tanvi Reddy | Scrum Master | PRJ-006 | Sprint 6 | 72 | 64 | 88.9 | 4 | 12 | 7.7 | Senior
Tanvi Reddy | Scrum Master | PRJ-006 | Sprint 7 | 80 | 69 | 86.2 | 5 | 11 | 5 | Junior
Tanvi Reddy | Scrum Master | PRJ-006 | Sprint 8 | 72 | 65 | 90.3 | 4 | 18 | 7.1 | Senior
Nikhil Rao | Developer | PRJ-001 | Sprint 1 | 78 | 68 | 87.2 | 7 | 15 | 5.3 | Junior
Nikhil Rao | Developer | PRJ-001 | Sprint 2 | 76 | 72 | 94.7 | 6 | 24 | 6.3 | Mid
Nikhil Rao | Developer | PRJ-001 | Sprint 3 | 74 | 68 | 91.9 | 6 | 9 | 3.3 | Senior
Nikhil Rao | Developer | PRJ-001 | Sprint 4 | 74 | 73 | 98.6 | 7 | 11 | 4.6 | Junior
Nikhil Rao | Developer | PRJ-001 | Sprint 5 | 75 | 64 | 85.3 | 4 | 17 | 2.4 | Senior
Nikhil Rao | Developer | PRJ-001 | Sprint 6 | 74 | 69 | 93.2 | 6 | 12 | 2 | Junior
Nikhil Rao | Developer | PRJ-001 | Sprint 7 | 80 | 72 | 90 | 6 | 10 | 3 | Mid
Nikhil Rao | Developer | PRJ-001 | Sprint 8 | 77 | 73 | 94.8 | 4 | 23 | 7.5 | Junior
Pooja Iyer | QA Engineer | PRJ-006 | Sprint 1 | 80 | 65 | 81.2 | 4 | 23 | 3.3 | Junior
Pooja Iyer | QA Engineer | PRJ-006 | Sprint 2 | 78 | 66 | 84.6 | 4 | 12 | 4.9 | Mid
Pooja Iyer | QA Engineer | PRJ-006 | Sprint 3 | 74 | 73 | 98.6 | 8 | 16 | 3 | Junior
Pooja Iyer | QA Engineer | PRJ-006 | Sprint 4 | 75 | 67 | 89.3 | 7 | 15 | 6.1 | Lead
Pooja Iyer | QA Engineer | PRJ-006 | Sprint 5 | 78 | 76 | 97.4 | 7 | 10 | 3.4 | Senior
Pooja Iyer | QA Engineer | PRJ-006 | Sprint 6 | 77 | 75 | 97.4 | 4 | 11 | 6.8 | Junior
Pooja Iyer | QA Engineer | PRJ-006 | Sprint 7 | 72 | 66 | 91.7 | 3 | 18 | 3.1 | Junior
Pooja Iyer | QA Engineer | PRJ-006 | Sprint 8 | 76 | 65 | 85.5 | 5 | 16 | 2.1 | Senior
Manish Dubey | Business Analyst | PRJ-002 | Sprint 1 | 77 | 63 | 81.8 | 4 | 19 | 4.3 | Senior
Manish Dubey | Business Analyst | PRJ-002 | Sprint 2 | 80 | 68 | 85 | 4 | 22 | 2.3 | Junior
Manish Dubey | Business Analyst | PRJ-002 | Sprint 3 | 77 | 67 | 87 | 4 | 10 | 7 | Lead
Manish Dubey | Business Analyst | PRJ-002 | Sprint 4 | 72 | 65 | 90.3 | 5 | 20 | 3.5 | Mid
Manish Dubey | Business Analyst | PRJ-002 | Sprint 5 | 73 | 60 | 82.2 | 3 | 13 | 3.3 | Senior
Manish Dubey | Business Analyst | PRJ-002 | Sprint 6 | 76 | 62 | 81.6 | 8 | 8 | 4.6 | Lead
Manish Dubey | Business Analyst | PRJ-002 | Sprint 7 | 73 | 71 | 97.3 | 8 | 19 | 5 | Lead
Manish Dubey | Business Analyst | PRJ-002 | Sprint 8 | 80 | 80 | 100 | 5 | 18 | 6.3 | Junior
Sneha Tiwari | Developer | PRJ-006 | Sprint 1 | 80 | 67 | 83.8 | 3 | 9 | 3.3 | Senior
Sneha Tiwari | Developer | PRJ-006 | Sprint 2 | 73 | 64 | 87.7 | 5 | 15 | 3.3 | Lead
Sneha Tiwari | Developer | PRJ-006 | Sprint 3 | 80 | 60 | 75 | 7 | 16 | 2.5 | Lead
Sneha Tiwari | Developer | PRJ-006 | Sprint 4 | 73 | 71 | 97.3 | 3 | 17 | 5 | Lead
Sneha Tiwari | Developer | PRJ-006 | Sprint 5 | 78 | 70 | 89.7 | 7 | 15 | 5.6 | Junior
Sneha Tiwari | Developer | PRJ-006 | Sprint 6 | 76 | 72 | 94.7 | 4 | 10 | 5.5 | Senior
Sneha Tiwari | Developer | PRJ-006 | Sprint 7 | 79 | 75 | 94.9 | 5 | 10 | 6.2 | Junior
Sneha Tiwari | Developer | PRJ-006 | Sprint 8 | 73 | 70 | 95.9 | 4 | 21 | 3.2 | Junior
Aryan Chopra | DevOps Engineer | PRJ-001 | Sprint 1 | 73 | 72 | 98.6 | 5 | 14 | 3.2 | Junior
Aryan Chopra | DevOps Engineer | PRJ-001 | Sprint 2 | 72 | 66 | 91.7 | 5 | 13 | 7 | Senior
Aryan Chopra | DevOps Engineer | PRJ-001 | Sprint 3 | 74 | 71 | 95.9 | 6 | 11 | 3.9 | Mid
Aryan Chopra | DevOps Engineer | PRJ-001 | Sprint 4 | 78 | 72 | 92.3 | 8 | 11 | 2.5 | Senior
Aryan Chopra | DevOps Engineer | PRJ-001 | Sprint 5 | 76 | 65 | 85.5 | 5 | 11 | 2.2 | Junior
Aryan Chopra | DevOps Engineer | PRJ-001 | Sprint 6 | 76 | 75 | 98.7 | 6 | 12 | 7.3 | Lead
Aryan Chopra | DevOps Engineer | PRJ-001 | Sprint 7 | 75 | 69 | 92 | 6 | 16 | 5 | Mid
Aryan Chopra | DevOps Engineer | PRJ-001 | Sprint 8 | 79 | 69 | 87.3 | 4 | 14 | 4 | Mid

## Milestones
Project ID | Milestone ID | Milestone Name | Planned Date | Actual Date | Status | Delivery Status
PRJ-001 | M1 | Requirements Finalized | 2025-01-25 | 2025-01-24 | Completed | On Time
PRJ-001 | M2 | UI Prototype Approved | 2025-02-28 | 2025-03-02 | Completed | Delayed
PRJ-001 | M3 | Backend APIs Complete | 2025-04-15 | 2025-04-14 | Completed | On Time
PRJ-001 | M4 | UAT Sign-off | 2025-05-30 | 2025-06-10 | Delayed | At Risk
PRJ-001 | M5 | Go Live | 2025-06-30 |  | Upcoming | On Track
PRJ-002 | M1 | Architecture Design Approved | 2025-02-20 | 2025-02-20 | Completed | On Time
PRJ-002 | M2 | Integration Testing Complete | 2025-04-10 | 2025-04-18 | Completed | Delayed
PRJ-002 | M3 | Security Audit Passed | 2025-05-15 |  | In Progress | At Risk
PRJ-002 | M4 | Pilot Launch | 2025-06-30 |  | Upcoming | At Risk
PRJ-006 | M1 | Data Collection Complete | 2025-02-15 | 2025-02-14 | Completed | On Time
PRJ-006 | M2 | Model v1 Training Done | 2025-03-20 | 2025-03-22 | Completed | Delayed
PRJ-006 | M3 | Beta Testing Complete | 2025-05-10 | 2025-05-12 | Completed | Delayed
PRJ-006 | M4 | Production Deployment | 2025-07-15 |  | Upcoming | On Track
PRJ-008 | M1 | API Spec Finalized | 2025-03-01 | 2025-02-28 | Completed | On Time
PRJ-008 | M2 | Developer Portal Live | 2025-04-15 | 2025-04-15 | Completed | On Time
PRJ-008 | M3 | Partner Onboarding Complete | 2025-06-15 |  | In Progress | On Track
PRJ-008 | M4 | Public Launch | 2025-07-31 |  | Upcoming | On Track
PRJ-004 | M1 | Data Audit Complete | 2025-03-30 | 2025-04-10 | Completed | Delayed
PRJ-004 | M2 | Migration Strategy Approved | 2025-05-01 |  | In Progress | At Risk
PRJ-004 | M3 | Pilot Migration Done | 2025-07-31 |  | Upcoming | At Risk

## 📖 PowerBI_Guide
AGILE PM DASHBOARD — POWER BI SETUP GUIDE
Created for Portfolio by Mehwish Shahzad
SHEET OVERVIEW
Projects | Master project list with RAG status, budget, and timeline
Sprints | Sprint-level velocity, story points, burndown data
Tasks | Individual tasks with cycle time, lead time, status, assignee
Risks_Issues | Risk register with severity, ownership, mitigation plans
Team_Capacity | Sprint-wise team utilization and productivity metrics
Milestones | Project milestones with planned vs actual delivery tracking
RECOMMENDED POWER BI PAGES
Page 1: Executive Overview | KPI cards: Total Projects, Avg Velocity, On-Time %, Budget Util%, Open Risks
Page 2: Sprint Performance | Line chart: Velocity trend ¦ Bar: Planned vs Completed ¦ Burndown chart
Page 3: Team Productivity | Stacked bar: Tasks by Status ¦ Donut: Workload by member ¦ Cycle/Lead Time
Page 4: Risk & Issues | Matrix: Risk Heat Map ¦ Bar: Open Risks by Severity ¦ Table: Aging issues
Page 5: Stakeholder View | Milestone tracker ¦ RAG status table ¦ Upcoming deliverables ¦ Gantt timeline
KEY DAX MEASURES TO CREATE
Sprint Velocity | AVERAGE(Sprints[Completed Story Points])
On-Time Delivery % | DIVIDE(COUNTROWS(FILTER(Milestones, Milestones[Delivery Status]="On Time")), COUNTROWS(Milestones))
Budget Utilization % | DIVIDE(SUM(Projects[Spent (₹)]), SUM(Projects[Budget (₹)]))
Sprint Predictability | AVERAGE(Sprints[Sprint Predictability %])
Open Risks Count | COUNTROWS(FILTER(Risks_Issues, Risks_Issues[Status]<>"Closed" && Risks_Issues[Status]<>"Mitigated"))